## Slide 1
DevOps Transformation - Status Report

## Slide 2
Agenda
2
3
4
1
Project Status Summary
Progress Since Last Report
5
Top Longer Term Milestones
Activities for the next period
Key Risks & Issues
6
7
Resource Onboarding / Burn Rate
Top Immediate Milestones

## Slide 3: Project Status Summary
Stream | Activities | Due date | Status
Resourcing | All the resource have started and there are as planned | 27/07/2015 | 
Design | Cucumber testing | 31/07/2015 | 
Design | Sonar integration for MCA | 31/07/2015 | 
Design | On boarding questioner finalization and the online portal | 24/07/2015 | 
Design | Complete conversation with Dom for the TEMS track and finalise plan | 21/07/2015 | 
Plan | Connect will 3 service owners (MCA/MCP & Cheque re-platforming) to encourage on boarding them on to the tool. | 20/07/2015 | 
Plan | Top 100 apps identification | 14/07/2015 | 
Build | Access for the tools / SW (Has been requested) | 15/07/2015 | 
Build | Laptop to all the technical team to start with the sprint and other activities planned | 21/07/2015 | 
Report Date | 30/07/2015 | Baseline Start | 01/07/2015 | Overall Status |  |  | 
Program Manager | Satish Bruno | Baseline Finish | 22/09/2015 | Schedule |  | Budget | 
Project Stage | Design / Plan / Build | Forecast Finish | 22/09/2015 | Resource |  | Quality | 
 |  |  |  | Scope |  | Risk | 
(R) Delayed: | (A) At Risk: | (G) On Target: | (P) Planning: | (C) Completed:

## Slide 4: Progress since last report
Task | % Complete | Remarks | Status
Platform |  |  | 
Workflow design using Jira vs. Jenkins | 50% | Evaluated the options in Jira and Jenkins | 
SSO integration design | 60% | Worked on the SSO integration | 
consideration/limitations in Jira, Jenkins | 100% | Evaluated the limitations | 
aPaaS blueprints integration | 80% | aPaaS blueprints integration with platform design | 
Application onboarding validation and webification | 100% | Launch application onboarding validation and webification | 
CI |  |  | 
Develop gradle script | 100% | Develop gradle script for automated build process | 
Converted to Gradle from Ant | 100% | Converted to Gradle from Ant for various components | 
Customized release plugins | 100% | Customized various release plugins to suit projects requirement | 
Code for java version blocker | 100% | Developed code for java version blocker | 
Workflows in Nolio | 100% | Analysed technical landscape and created workflows in Nolio | 
MCA & MCP - automate build script using gradle | 60% | Examined MCA & MCP application and suggested best way to automate build script using gradle | 
Discovery phase with Barclays.net | 60% | Conducted discovery phase with Barclays.net | 
Chef cookbook for Nolio | 100% | Created Chef cookbook for Nolio | 
Jira Workflow for PCBDevOps | 100% | Created Jira Workflow for PCBDevOps | 
Notes: Segrigate as Devops Tems and SV

## Slide 5: Progress since last report
Task | % Complete | Remarks | Status
TEMS |  |  | 
SV |  |  | 
Initial discussion with key stakeholders | 100% | Initial discussion with stakeholder completed | 
Identified 3 applications for initial analysis/pilot implementation (CHUB, PBTV, CDI) | 100% | Identify application to be worked on | 
Initial discussion with CHUB & CDI provider application group | 100% |  | 
questionnaire(virtualisation) to obtain service operation details | 100% | Shared questionnaire(virtualisation) to obtain service operation details from CHUB team | 
Machine to setup Parasoft virtualise built | 60% | Sorin working on it | 
Notes: Segrigate as Devops Tems and SV

## Slide 6: Progress since last report
Task | % Complete | Remarks | Status
Detailed discussion and the Demo for DOM | 100% | Plan reviewed and agreed | 
Collated and categorized the tooling requirements. | 100% | Tooling that need to be used has been finalized | 
Resource On boarding | 100% | All the resource except for 1 CI engineer at onsite on boarded | 
Operating model for platform components | 80% | Its been worked upon and will be completed in coming week | 
MRA application onboarding in progress. | 70% | Outside of the scope of pilot applications but a good real time perspective | 
MCA on Boarded | 80% | MCA has been a significant win this week, with 19 applications now on boarded and utilising the tools. | 
Cheque Re-Platforming | 60% | Since this is new service there are no application to be on boarded at this point in time. All the tools they are using are central one. | 
MCP on Boarding | 30% | Using their own Build framework and the tools | 
Notes: Segrigate as Devops Tems and SV

## Slide 7: Key Activities for the Next Period
Working on creating the deployment process flow for BO component
High level start up dependency and deployment dependency workflow for Barclays.net.
JIRA and Nolio integration
Moving applications to central Jenkins and Nolio
Commence next 100 applications, on boarding questionnaire to be sent out to next set of services
Work on ApaaS solution
CI
Maturity assessment + onboarding integration with dashboarding
Onboarding design blueprint for third party software (like strategic billing)
Jira authentication and Jenkins workflow integration
Environments HLD design and integration with DevOps TOM
Platform

## Slide 8: Key Activities for the Next Period
Look at DevOps and TEMS interface
Unified tooling for environment booking
TEMS tool - JIRA integration
Identify gaps in current operation of services based on finalized catalogue and current state assessment of sample apps
Define target operating model to operate the services finalized in TO-BE catalogue
Plan pilot operations for AS – IS transition followed by transformation
TEMS
Obtain CHUB-ODM service details, required files, request/response pairs, endpoint details to virtualise
Initiate discussion and obtain service details with application groups (like MCP, MCA, BEM, BEM ETL, Strategic Billing)
Share questionnaire(virtualisation) to obtain service operation details from PBTV application group
Update application onboarding questionnaire for CHUB(Final Version)
Analyse the discovery inputs and assess maturity level, standards and process
Finalise version control and central repository tools for Parasoft virtual components and related artifacts
Analyse systems dependencies and challenges
Update project plan and review Checkpoint on POC scope and current status
Define SV approach, standards and processes; update plan
SV

## Slide 9: Top Immediate Milestones
No. | Milestone | Due Date | Status | Remarks
1 | On-board MCA to all the tools | 31/07/2015 |  | All application of MCA have been on boarded to the strategic tools identified in their local version. They are Performing POC for some of the central tools
2 | On-board MCP to all the tools | 31/07/2015 |  | MCP are using some of the strategic tool set, but at the moment they are shortage of staff to pickup the activity to move to central tools.
3 | On-board cheque re-platforming to all the tools | 31/07/2015 |  | Since this is new service there are no application to be on boarded at this point in time. All the tools they are using are central one.
4 | Confirm on the billing for the Lead SA | 30/07/2015 |  | Ivor has been informed and partial agreement is in place.
5 | Unified tooling requirement to be discussed and agreed | 4/08/2015 |  | Get Dom’s time for Tuesday.
Milestones
Notes: Need TEMS and SV representation as well

## Slide 10: Top Longer Term Milestones
No. | Milestone | Due Date | Status | Remarks
1 | Start discussion with the 100 Apps service owners | 03/08/2015 |  | The list has been collated and completed, the initial questioner need to be circulated
2 | Align short term transactional deliverables with the broader deliverables called out in the SoW | 31/07/2015 |  | Show some example for the what we are doing and what we have been agreed to do.
3 |  |  |  | 
4 |  |  |  | 
Milestones

## Slide 11: Key Risks & Issues
Description | Likelihood | Impact | Mitigation | Status | Owner
Sarav travel is delayed due to delay in WP approval from embassy | Likely | High | Working from offshore during UK hrs. Kaushik to look at alternative resources | In Progress | Kaushik

## Slide 12: Key Risks & Issues
Description | Likelihood | Impact | Mitigation | Status | Owner
SOW agreement and the activities that are being assigned are not aligned | Likely | high | Realign the SoW as per the current plan by Barclays | In Progress | Bruno
Sarav travel is delayed due to delay in WP approval from embassy | Likely | Medium | Working from offshore during UK hrs. Cognizant Immigration team has communicated to embassy to expedite the processing. | In Progress | Sarav

## Slide 13
Thank You!